## Time Tracking Report.xls
Issue Type | Key | Status | Summary | Original Time Estimated (hr) | Total Time Spent (hr) | Accuracy
Task | WCFF-10 | Resolved | Initial Setup Mockup | 0 | 0 | 0.00
Story | WCFF-100 | Resolved | As a user, I can click a ministry to see information about the ministry | 13 | 8 | 5.00
-> Sub-task | WCFF-101 | Resolved | -> Bigger gaps between cards | 1 | 5.5 | -4.50
-> Sub-task | WCFF-102 | Resolved | -> Create screen to ask user if offering or riding | 0 | 0 | 0.00
-> Sub-task | WCFF-103 | Resolved | -> Make ministries clickable | 2 | 1 | 1.00
-> Sub-task | WCFF-104 | Resolved | -> Create a generic form that can be given to the UI | 5 | 5.5 | -0.50
-> Sub-task | WCFF-105 | Resolved | -> Make ministry info screen | 4 | 5 | -1.00
-> Sub-task | WCFF-106 | Resolved | -> Push created rides to the database | 0 | 2 | -2.00
-> Sub-task | WCFF-108 | Closed | -> Store a user's rides on the phone | 5 | 4.0167 | 0.98
-> Sub-task | WCFF-109 | Resolved | -> Link the ridesharing tab to the ridsharing UI | 0 | 1 | -1.00
Epic | WCFF-11 | Resolved | Balsamiq Mockups | 0 | 0 | 0.00
Bug | WCFF-110 | Resolved | Delete ministry prefs after de-selecting a campus | 2 | 5 | -3.00
-> Sub-task | WCFF-111 | Resolved | -> Link the ridesharing button to the ridesharing tab | 0 | 2 | -2.00
-> Sub-task | WCFF-112 | Resolved | -> Allow user to go back from ministries to campuses on initial setup | 1 | 0.083333 | 0.92
-> Sub-task | WCFF-113 | Resolved | -> UI for viewing events that have ridesharing enabled | 0 | 3 | -3.00
-> Sub-task | WCFF-114 | Closed | -> UI for I can ride or I can drive after clicking event | 0 | 0 | 0.00
-> Sub-task | WCFF-115 | Resolved | -> Retrieve rides for an event from the database | 0 | 4 | -4.00
-> Sub-task | WCFF-116 | Resolved | -> UI for list of rides in database for event | 0 | 10 | -10.00
-> Sub-task | WCFF-117 | Resolved | -> Interrupt and skip fade animation in initial setup. | 3 | 1.25 | 1.75
Task | WCFF-119 | Resolved | Add comments to my code from Sprint1 | 2 | 1.1667 | 0.83
Task | WCFF-12 | Closed | Get Involved Mockup | 0 | 0 | 0.00
Task | WCFF-13 | Resolved | Resources Mockup | 0 | 0 | 0.00
-> Sub-task | WCFF-133 | Resolved | -> Update rides in the database when a user signs up for a ride | 0 | 2 | -2.00
Task | WCFF-14 | Closed | Build & Dev Environment | 0 | 0 | 0.00
Task | WCFF-146 | Resolved | Cache information pulled from the database | 0 | 0 | 0.00
Task | WCFF-15 | Resolved | Set up Continuous Integration (Bamboo?) | 0 | 0 | 0.00
-> Sub-task | WCFF-150 | Resolved | -> Finish New Ride Pushing | 5 | 0 | 5.00
-> Sub-task | WCFF-152 | Resolved | -> Save & Autofill the user's name | 2 | 2.5 | -0.50
-> Sub-task | WCFF-158 | Resolved | -> Delete passengers from a ride in the database | 3 | 2 | 1.00
Task | WCFF-16 | Resolved | Set up Git repository on Bitbucket | 0 | 0 | 0.00
-> Sub-task | WCFF-160 | Resolved | -> Create logic for sorting/searching | 4 | 2 | 2.00
Task | WCFF-163 | Resolved | Event and Summer Mission event image sizes keep same | 0 | 0.5 | -0.50
-> Sub-task | WCFF-17 | Resolved | -> Create Instructions | 0 | 0 | 0.00
Task | WCFF-19 | Closed | QA Document | 0 | 0 | 0.00
Task | WCFF-2 | Resolved | Requirements Sample | 0 | 0 | 0.00
Task | WCFF-20 | Resolved | Class UML Diagram | 0 | 0 | 0.00
Task | WCFF-21 | Closed | Sequence UML Diagram | 0 | 0 | 0.00
Task | WCFF-22 | Closed | Create UI For Prototype | 0 | 0 | 0.00
Task | WCFF-23 | Closed | Validation Plan (QA Plan) | 0 | 0 | 0.00
Task | WCFF-24 | Closed | Vertical Prototype (DB component) | 0 | 3 | -3.00
Task | WCFF-25 | Closed | Final SRS | 0 | 0 | 0.00
Task | WCFF-26 | Closed | Software Architecture v2 | 0 | 0 | 0.00
Task | WCFF-27 | Closed | Requirements Traceability Matrix | 0 | 0 | 0.00
Task | WCFF-28 | Resolved | Vertical Prototype (SMS component) | 0 | 0 | 0.00
Task | WCFF-29 | Closed | Youtube Api | 0 | 0 | 0.00
Task | WCFF-30 | Resolved | Push Notifications | 0 | 0 | 0.00
Task | WCFF-31 | Resolved | Integrate Calendar API into the vertical prototype | 0 | 0 | 0.00
Task | WCFF-32 | Closed | Push Notification to other phones | 0 | 0 | 0.00
Task | WCFF-33 | Resolved | Add side bar to UI | 0 | 0 | 0.00
Task | WCFF-34 | Closed | Update Sequence Diagrams (Event) and Class Diagrams (Ministries) | 0 | 0 | 0.00
Task | WCFF-36 | Closed | Review Brian Quezada Architecture sections | 0 | 0 | 0.00
Story | WCFF-37 | Resolved | As a student user, I can view a welcome screen to introduce the application | 5 | 0 | 5.00
Story | WCFF-38 | Resolved | As a student, I can select campuses to join | 0 | 11.5 | -11.50
Story | WCFF-39 | Resolved | As a student, I can select ministries to subscribe to | 13 | 13.25 | -0.25
Story | WCFF-40 | Resolved | As a student, I can view summary, campus, image about ministries | 5 | 0.3 | 4.70
Story | WCFF-41 | Resolved | As a student, I can change my campuses and ministries in a settings tab | 5 | 7.1667 | -2.17
Story | WCFF-42 | Resolved | As a user, I can view a list of upcoming events from my subscribed ministries | 8 | 18 | -10.00
Story | WCFF-43 | Resolved | As a user, I can select an event and view image, time, location, ministry, description | 13 | 19 | -6.00
Story | WCFF-44 | Resolved | As a user, I can add an event to my calendar | 13 | 13 | 0.00
Story | WCFF-45 | Closed | As a user, I can view a settings tab | 5 | 6 | -1.00
Story | WCFF-46 | Resolved | As a user, I can receive a push notification from an admin to a specific ministry for a ministry event | 5 | 4 | 1.00
Story | WCFF-48 | Resolved | As a user, I can view a list of Summer Missions from the cru db | 8 | 9 | -1.00
Story | WCFF-49 | Resolved | As a user, I can view the location, date, image of a summer mission | 8 | 8 | 0.00
Task | WCFF-5 | Resolved | Systems Requirement Specification | 0 | 0 | 0.00
-> Sub-task | WCFF-50 | Resolved | -> Retrieve campus information from the database | 0 | 3 | -3.00
-> Sub-task | WCFF-51 | Resolved | -> Display list of campuses in a card layout | 0 | 2.5 | -2.50
-> Sub-task | WCFF-52 | Resolved | -> Retrieve list of ministry information from database | 0 | 0 | 0.00
-> Sub-task | WCFF-53 | Closed | -> Display list of ministries in a card layout | 0 | 2 | -2.00
-> Sub-task | WCFF-54 | Closed | -> Save the campus selections to the app | 0 | 4 | -4.00
-> Sub-task | WCFF-55 | Resolved | -> Save the ministry selections to the app | 0 | 2 | -2.00
-> Sub-task | WCFF-56 | Resolved | -> Retrieve info from db | 0 | 6.5 | -6.50
-> Sub-task | WCFF-57 | Resolved | -> Display event info | 0 | 12 | -12.00
-> Sub-task | WCFF-58 | Closed | -> Add button to event page for add to calendar | 0 | 0.083333 | -0.08
Task | WCFF-59 | Resolved | Initial Cleanup | 8 | 10 | -2.00
Task | WCFF-6 | Resolved | Vision and Scope | 0 | 0 | 0.00
Task | WCFF-60 | Resolved | Create UML & Doc explaining database retreival | 0.016667 | 0 | 0.02
Task | WCFF-61 | Closed | Create UML & Doc explaining database retreival | 0 | 0 | 0.00
Task | WCFF-62 | Closed | Save events to the app | 0 | 0 | 0.00
Task | WCFF-63 | Closed | Create consistent/persistent logs | 4 | 3 | 1.00
-> Sub-task | WCFF-66 | Resolved | -> Update CalendarEvent and CalendarAccessor | 1 | 1.0167 | -0.02
Task | WCFF-7 | Resolved | Ride Sharing Mockup | 0 | 0 | 0.00
Task | WCFF-70 | Resolved | Make back buttons work | 0 | 1 | -1.00
-> Sub-task | WCFF-72 | Resolved | -> Link UI to calendar event creator | 1 | 1.5 | -0.50
-> Sub-task | WCFF-73 | Resolved | -> Save calendar event ids locally | 3 | 2.5 | 0.50
-> Sub-task | WCFF-74 | Resolved | -> Keep UI "add event" button blue after adding event | 1 | 2 | -1.00
-> Sub-task | WCFF-75 | Resolved | -> Change calendar event reminder time to match time in database | 1 | 2 | -1.00
-> Sub-task | WCFF-76 | Resolved | -> Delete event on deselect of the "add to calendar" button | 1 | 3.05 | -2.05
Bug | WCFF-77 | Resolved | Event times are in military time | 1 | 0.16667 | 0.83
Task | WCFF-8 | Resolved | Events Mockup | 0 | 0 | 0.00
Task | WCFF-80 | Resolved | Screens that display cards should use the same code | 8 | 0 | 8.00
-> Sub-task | WCFF-81 | Resolved | -> Use Cru Fonts | 2 | 4 | -2.00
Task | WCFF-83 | Resolved | UI Overhaul | 21 | 43 | -22.00
-> Sub-task | WCFF-84 | Resolved | -> Change colors to Cru Colors | 0 | 6 | -6.00
Story | WCFF-87 | Resolved | As a user, I can see a list of rides for an event | 8 | 17 | -9.00
Task | WCFF-9 | Resolved | Summer Missions Mockup | 0 | 0 | 0.00
-> Sub-task | WCFF-93 | Resolved | -> Event images fill screen | 0 | 1.5 | -1.50
-> Sub-task | WCFF-94 | Resolved | -> Event whole screen scrolls | 0 | 2.5 | -2.50
-> Sub-task | WCFF-95 | Resolved | -> Make checkboxes for initial setup not pink | 1 | 1 | 0.00
-> Sub-task | WCFF-96 | Resolved | -> Calendar button not grey | 0 | 0.16667 | -0.17
-> Sub-task | WCFF-98 | Resolved | -> Splash Screen Overhaul | 0 | 7 | -7.00
-> Sub-task | WCFF-99 | Resolved | -> Make cards prettier | 0 | 9 | -9.00

## Results
Issue Type | Key | Status | Summary | Original Time Estimated (hr) | Total Time Spent (hr) | Accuracy
|  |  | Total | 201.02 | 329.22 | -128.20